## Sheet1
Sprint / Week | Start Date | End Date | Role | Activities | Deliverables | Owner
Week 1 | 2025-12-30 | 2026-01-05 | Planning & Assignment | Project planning, task breakdown, sprint allocation, defining milestones | Sprint plan document, task assignment sheet, roadmap finalized | Shaarav
Week 2 | 2026-01-06 | 2026-01-12 | Training & Frontend Follow-up | Provide AI training resources, guide team on agent training, review frontend progress | Training material shared, frontend status review report | Shaarav
Week 3 | 2026-01-13 | 2026-01-19 | Backend Follow-up & Coordination Handover | Monitor backend architecture progress, resolve blockers, handover coordination to Amrita | Backend progress validation, coordination transition completed | Shaarav
Week 4 | 2026-01-20 | 2026-01-26 | Integration Phase 1 | Begin integration of backend tools with frontend APIs, test connectivity | Initial integration completed, API linkage validated | Shaarav
Week 5 | 2026-01-27 | 2026-02-02 | Integration Phase 2 | Refine integration, debugging, synchronization testing | Stable backend-frontend communication established | Shaarav
Week 6 | 2026-02-03 | 2026-02-09 | Final Integration & Testing | System-wide integration testing, performance validation, final adjustments | Integrated system ready for deployment/testing | Shaarav
Week 7 | 2026-02-10 | 2026-02-16 | Production, Testing and Deployment | Ensure the project gets run onto production and finally deploy | Deploy project over website | Shaarav
Week 8 & 9 | 2026-02-16 | 2026-02-27 | Preparation for Presentation | Make preparations for final showcase of project | Prepare presenations and demo video for project | Shaarav